## Version 1
Team Member Name | Role | Primary Responsibilities | Current Tasks | Status (Not Started / In Progress / Done) | Notes / Blockers
Herby Hertilien | Scrum Master | Planning, scope control, diagram coordination, integration oversight | Github repo, task separation spreadsheet, Initial diagrams and planning document, update sheets | Complete
Joshua Frederick | Backend Developer | API development, database models, authentication | Database creation | Complete
| Backend Developer | Upload logic, ownership rules, testing |  | Complete
Jacob Ahrens | Frontend Developer | Board pages, poster grid, upload UI | Create V1 of Frontend | Complete
|  |  | Test Frontend compatibility | Complete
|  |  | Connect with Backend APIs | Complete | Waiting for backend API endpoints to be availible
Miaoqin Xu | DevOps Engineer | Docker, Cloud Run, Cloud SQL, CI/CD | Create Dockerfile for frontend & backend, Create docker-compose.yml for deployment | Complete | Waiting for backend code to test full docker compose setup
Daniel Muskat | Content / Data Lead | Create poster images, define boards, seed data | Gather posters for demo and testing | Complete
Kelly Rojas | Middleware | Testing team |  | Complete | Join Herby, and Miaoqin Xu

## Version 2
Team Member Name | Role | Primary Responsibilities | Current Tasks | Status (Not Started / In Progress / Done) | Notes / Blockers
Herby Hertilien | Scrum Master | Planning, scope control, diagram coordination, integration oversight | Github repo, task separation spreadsheet, Initial diagrams and planning document, update sheets | Complete
Joshua Frederick | Backend Developer | API development, database models, authentication | Data Metrics needed | Complete
| Backend Developer | Upload logic, ownership rules, testing | Stress stests needed | Complete
Jacob Ahrens | Frontend Developer | Board pages, poster grid, upload UI | Issue Tracker and Functions Report | Complete
|  |  | Tags for individual posts (premade tags) | Complete
|  |  | share button | Complete
Miaoqin Xu | DevOps Engineer | Docker, Cloud Run, Cloud SQL, CI/CD |  | Complete
Daniel Muskat | Content / Data Lead | User Testing / Final report | User Testing / Final report | Complete
Kelly Rojas | Middleware | User Testing / Final report | User Testing / Final reporti | Complete